## Product Roadmap
Agile Product Roadmap
<Agile Development Project> | Q2 |  |  | Q3 |  |  | Q4
| February | March | April | May | June | July | August | September | October
Group 1
Manufacturer
Group 3
Group 4
Group 5
Create an Agile Product Roadmap in Smartsheet
Product 2

## Project Charter
Agile Project Charter
General Project Information
Project Name | Inventory Management System
Project Champion | Wong Kwun Hoi
Project Sponsor | ABC Manufacturer
Project Manager | Jeffrey Lo Ho Tin
Stakeholders | Manufacturer, Online Retailer & Logistics compnay
Expected Start Date | 2019-02-15
Expected Completion Date | 2019-04-05
OK
Project Details
Mission | As a Manufacturer company, we will work together as a team to produce the products that are ordered from the online retailer and pack it to the logistics company
Scope | The scope of the project is providing a better user interface to monitor the stock management level & simple application to exchange data between online retailer and manufacturer
Success Metrics | 1.) Succesfully import json data from the online retailer into our database. 2.)export the same format of json data to the logistics company. 3.) Having a website catalog for the cusomters to order the products
Date:15/2/2019 | Date: 5/4/2019

## Project Plan
Agile Project Plan
Project Name | Inventory Management System
Project Manager | Jeffrey Lo
Project Deliverable | 1.) Develop a stock monitoring system 2.) Develop a website catalog which shows the products that we produce 3.) Deliever a payment and scheduling system
Scope Statement | Inventory Management System
Start Date | 2019-02-15
End Date | 2019-05-01
Overall Progress | 80%
Task Name | Responsible | Start | End | Days | Status
Sprint 1 | Toby Chan | 2019-02-15 | 2019-03-08 | 21 | Complete
Stock monitoring system: Importing json data into our database | Ivan Wong & Wong Kwun Hoi | 2019-02-15 | 2019-03-01 | 14 | Complete
Stock monitoring system: Exporting json data to the logistics | Toby Chan | 2016-03-01 | 2016-03-08 | 7 | Complete
Sprint 2 | Ivan Wong | 2019-03-08 | 2019-03-21 | 13 | Complete
Developing a website catalog to show our product | Jeffrey Lo | 2019-03-08 | 2019-03-14 | 6 | Complete
On the website catalog, provide a enquiry option for customers to express their interest to the product | Mark Kwok | 2019-03-14 | 2019-03-20 | 6 | Complete
On the website catalog, besides ordering option, provide select box for customers to choose the qunatity of the products | Ivan Wong & Wong Kwun Hoi | 2019-03-14 | 2019-03-20 | 6 | Complete
On the website catalog, develop a production planning system | Ivan Wong & Jeffrey Lo | 2019-03-14 | 2019-03-21 | 7 | Complete
Sprint 3 | Wong Kwun Hoi | 2019-03-20 | 2019-04-20 | 31 | In-progress
Developing a payment confirmation system | Jeffrey Lo | 2019-03-20 | 2019-04-15 | 26 | In-progress
Developing a Transportation and Delivery Scheduling system | Mark Kwok | 2019-03-20 | 2019-04-15 | 26 | In-progress
finalize and merge the payment and scheduling system | Wong Kwun Hoi | 2019-03-31 | 2019-04-15 | 15 | In-progress
Create an Agile Project Plan in Smartsheet
Formulas:
Start = [Start, row below]

## User Story
Agile User Story Template
Feature | User Story ID | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal>
1 | 1 | manufacturer | I want to develop a production planning system | so I can meet the market demand
1 | 2 | manufacturer | I want to stock the products inside the warehourse | so I can keep track on stock records
2 | 3 | manufacturer | I want to publish a catalog website | so my customer can check on the catalog of my product more easily
2 | 4 | Retailer | I want to send enquiry for the manufacture product | so I can obtain the information and express my interest to the products of manufactures
2 | 5 | manufacturer | I want to confirm order from online retailer | so I can confim the further details of order, such as amount of the products
1 | 6 | manufacturer | I want to develop a stock mannaging system | so I can receive the required data from customer and put it in my database
1 | 7 | manufacturer | I want to check the stock level using the stock mannaging system | so I could arrange and produce products for customer within requirement
3 | 8 | manufacturer | I want to arrange shipping information in the stock mannaging system | so I could keep record of product flow andnotice for ourdelivery plan for logistics.
3 | 9 | manufacturer | I want to export shipping information to the logistics company | so I could provide deliever information for the logistics company help me deliever my product to my customer.
Track Agile User Stories in Smartsheet

## Sprint Backlog
Sprint Backlog Template ( Remaining outstanding efforts in hours )
Sprint Number | 1
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
User Story #1 | 10 | Mark Kwok | Complete
Investigating market trends | 5 | Mark Kwok | Complete | 4 | 4 | 3 | 2 | 1 | 0 | 0
Receive market response | 5 | Mark Kwok | Complete | 4 | 4 | 3 | 2 | 1 | 0 | 0
User Story #2 | 25 | Toby Chan | Incomeplete
Develop a stock monitoring system | 30 | Toby Chan | Incomeplete | 24 | 20 | 16 | 10 | 4 | 2 | 0
User Story #3 | 20 | Ivan Wong | Complete
Develop a website catalog to display the products that we produce | 10 | Ivan Wong | Complete | 16 | 14 | 10 | 6 | 3 | 2 | 0
User Story #4 | 5 | Jeffrey Lo | Complete
On the website catalog, provide a ordering option for customers to order the products | 5 | Jeffrey Lo | Complete | 4 | 2 | 0 | 0 | 0 | 0 | 0
User Story #5 | 5 | Jeffrey Lo | Complete
On the website catalog, besides ordering option, provide select box for customers to choose the qunatity of the products | 5 | Jeffrey Lo | Complete | 6 | 5 | 4 | 3 | 2 | 1 | 0
User Story #6 | 10 | Jeffrey Lo | Complete
On the website catalog, develop a production planning system | 5 | Ivan Wong | Complete | 5 | 5 | 3 | 1 | 0 | 0 | 0
User Story #7 | 10 | Wong Kwun Hoi | Incomeplete
Developing a payment confirmation system (stage 1) | 5 | Wong Kwun Hoi | Incomeplete | 12 | 9 | 7 | 5 | 4 | 0 | 0
Developing a payment confirmation system (stage 2) | 5 | Wong Kwun Hoi | Incomplete | 14 | 10 | 7 | 3 | 2 | 1 | 0
User Story #8 | 10 | Toby Chan | Incomeplete
Developing a Transportation and Delivery Scheduling system | 10 | Toby Chan | Incomeplete | 18 | 15 | 10 | 6 | 4 | 2 | 0
User Story #9 | 10 | Ivan Wong | Incomeplete
finalize and merge the payment and scheduling system | 10 | Ivan Wong | Incomeplete | 8 | 6 | 2 | 0 | 0 | 0 | 0
Total | 100 |  |  | 107 | 66 | 59 | 34 | 19 | 8 | 0

## Test Plan
Agile Test Plan
Project Name | Inventory Management System |  | Browser: | Python, Html, Css
Test Case ID |  |  | Version:
Written By: | Toby Chan, Ivan Wong, Jeffrey Lo |  | Description: | Testing on our inventory management system
Tested By: | Mark Kwok |  | Tested On: | Personal Computer and Notebooks
Test # | Date | Action | Expected Results | Actual Results | Pass?
1 | 2019-02-25 | Read json file | Select json file for input data source | Retrieve onlinw json file for source file using python
2 | 2019-02-26 | Decode json data | Read and list all data in json file | Listing out all data with dict
3 | 2019-02-27 | Insert into database | Insert successful | Insert successful
4 | 2019-02-27 | Prevent duplicated data input | duplicate data input from source data was prevented using sql coding | duplicate data input from source data was prevented using sql command 'ignore'
5 | 2019-02-27 | Query all rows of data in database | Display as a list | Display as a list
6 | 2019-02-27 | Generate CSV file | Write column name and data into file | Write column name and data into file
7 | 2019-02-28 | Add file type selection function | Available to select data file or online data
8 | 2019-02-28 | Use another table for exporting data to logistics | Call out and display all data in table in list form
9 | 2019-03-01
10 | 2019-03-02
11 | 2019-03-03
2019-03-04
2019-03-05
2019-03-06
Create a Test Plan in Smartsheet

## Product Backlog
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | Yes | Yes | High | Complete | 80 | Yes
Stock monitoring system: Importing json data into our database | Yes | Yes | High | Complete | 40 | Yes
Stock monitoring system:Exporting json data to the logistics | Yes | Yes | High | Complete | 40 | Yes
Sprint 2 | Yes | Yes | Medium | Complete | 90 | Yes
Developing a website catalog to show our product | Yes | Yes | Medium | Complete | 30 | Yes
On the website catalog, provide a ordering option for customers to order the products | Yes | Yes | Medium | Complete | 20 | Yes
On the website catalog, besides ordering option, provide select box for customers to choose the quantity of the products | Yes | Yes | Medium | Complete | 20 | Yes
On the website catalog, develop a production planning system | Yes | Yes | Medium | Complete | 20 | Yes
Sprint 3 | No | No | Low | In Progress | 24 | Yes
Developing a payment confirmation system | No | No | Low | In Progress | 8 | Yes
Developing a Transportation and Delivery Scheduling system | No | No | Low | In Progress | 8 | Yes
finalize and merge the payment and scheduling system | No | No | Low | In Progress | 8 | Yes

## Release Plan
Agile Release Plan
Sprint | Task | Start | End | Duration | Status | Release Date | Goal
1 (Stock Monitoring System) | Adding import and export function from the database | 2019-02-01 | 2019-02-02 | 1 | Released | 2019-02-02
1 | Adding order checking function | 2019-02-02 | 2019-02-03 | 1 | Released | 2019-02-03
1 | Adding stock level checking function | 2019-02-04 | 2019-02-05 | 1 | Released | 2019-02-04
1 | Adding shipment timing information | 2019-02-05 | 2019-02-06 | 1 | Released | 2019-02-06
1 | Testing the Stock Monitoring System | 2019-02-07 | 2019-02-11 | 4 | Released | 2019-02-11 | Find out the potential problems
1 | Debug the potential problems found in testing | 2019-02-12 | 2019-02-15 | 3 | Released | 2019-02-15 | Fix the potential problems
1 | Testing the the Stock Monitoring System | 2019-02-15 | 2019-02-15 | 0 | Released | 2019-02-15 | Make sure the potential problems are fixed
2 (Website Catalog) | Coding HTML for the website base | 2019-02-19 | 2019-02-21 | 2 | Released | 2019-02-21
2 | Coding CSS and PHP for the website | 2019-02-21 | 2019-02-23 | 2 | Released | 2019-02-23
2 | Adding ordering function in the Website Catalog | 2019-02-24 | 2019-02-25 | 1 | Released | 2019-02-25 | Use for customers to order the products
2 | Adding select box in the Website Catalog | 2019-02-25 | 2019-02-26 | 1 | Released | 2019-02-26 | Use for customers to choose the quantity of the products
2 | Import image to the Website Catalog | 2019-02-26 | 2019-02-26 | 0 | Released | 2019-02-26
2 | Develop the production planning system | 2019-02-27 | 2019-03-02 | 3 | Released | 2019-03-02
0
0
0
0
0
0